## Marketplace_Active
Bug ID | Sections | Test Case | Steps | Expected | Actual | Status | Part | Bug Priority | Repeated Bugs | Branch Name
1 | Solutions Upload -> Business Needs Addressed | Business Needs Addressed in Solution Update | In Solution Update | Business Needs Addressed should be in bullet form as on mosaicthings.lntinfotech.com | Currently Business Needs Addressed are sperated with comma | Active | Ajay | Minor
2 | My Profile Section - >Password Settings | Update Password Button is not working | https://ltimosaicthingsdev.azurewebsites.net/myprofile | Update Password Button when clicked should through toast message it is updated successfully or not | Currently there is no notification when button clicked so user gets confused whether password is updated or not | Resolved | Ajay | Major
3 | My Profile Section - >Password Settings | Current Password Field | https://ltimosaicthingsdev.azurewebsites.net/myprofile | when previous password matches with password that is putting through by user then only it should insert the password or it should provide toast message that current password should match the password inserted | Currently current password is not matching with typed password | Resolved | Ajay/Satej | Major
4 | Approval Management -> Partners Form --> Company Name Field | Company Name in Approval Management Partners Form | https://ltimosaicthingsdev.azurewebsites.net/approval | It should accept Space, special characters and numbers | Only accepting alphabets | Resolved | Ajay | Minor
5 | Solution Edit Button -> Company Field | Company Field | https://ltimosaicthingsdev.azurewebsites.net/description/167 | After clicking edit button Company field should be filled with previously uploaded data | Currently Company field is empty, Every time I need to fill that company and then only I goes for approval in next stage | Active | Ajay | Major
6 | Marketplace -> Solution Tiles | Solution Tiles in MarketPlace | https://ltimosaicthingsdev.azurewebsites.net/solution | There is no upload for logoImageUrl in solution through solution upload form | Curretly Solution title distorted due to non availability of logoImageUrl | Active | Ajay/Satej | Major
7 | Marketplace -> landing | Subscribe For Updates | http://mosaicthings.lntinfotech.com/landing | Subscribe link when clicked from email should redirect to ltimosaicthingsdev.azurewebsites.net for confirmation | Currently it is redirecting to ltimosaicthingsdev.azureedge.net | Active | Ajay | Major
8 | Contact Form -> Message Field | on button click you guys can check, Message Field in Contact Form | https://ltimosaicthingsdev.azurewebsites.net/contact | Message Field should consist of all special character and numbers | When there are special characters and numbers in the message field so it is not posting contact registry to database on click on contact form submit button. | Active | Ajay | Major
9 | M2MCM -> LTI Solutions -> Hybrid Network Solutions (GSM, WLAN, Zigbee, LoRa) | Hybrid Network Solutions (GSM, WLAN, Zigbee, LoRa) in M2MCM | https://ltimosaicthingsdev.azurewebsites.net/icm | Should not overlap the text | Currently overlaping the text | Active | Ajay | Major
10 | MarketPlace -> upload | Hardware upload sideways to solution upload | https://ltimosaicthingsdev.azurewebsites.net/solution | Hardware Upload section is sideways to solution upload section | Hardware upload section is missing, only solution upload section is there. | Active | Ajay | Major
11 | Marketplace -> Search Functionality | Search Functionality | https://ltimosaicthingsdev.azurewebsites.net/solution | provide result for all combination of words | Currently Api throw internal server error when 2 words searched simultaneously | Active | Satej | Major
12 | Login -> LTI USER LOGIN | LTI USER LOGIN TEXT | https://ltimosaicthingsdev.azurewebsites.net/signin | LTI user login button text should be centrally aligned | Text is right aligned currently | Active | Ajay | Minor
13 | Landing Page | Readability Issue | Whole Website |  | Currently Readability issue is there with same font on the website | Active | Ajay | Major
14 | Footer -> Youtube icon | Youtube Red Icon | Whole Website | Youtube icon should be white to maintain the uniformity in website | Youtube is icon is red curretly | Active | Ajay | Major
15 | Any Solution -> Request For Demo | Request For Demo Functionality | Any Solution | Request For Demo should submit data to database after button click | Currently Internal Server Error | Active | Satej | Major
16 | Any Solution -> Request For Demo | Message field | Any Solution | Message field marked with red dot as mandatory | Not marked as red dot currently | Active | Ajay | Minor
17 | Any Solution -> Request For PoC -> PoC Name Field | PoC Name Field | Any Solution PoC Form | It should accept Space, special characters and numbers | Only accepting alphabets | Active | Ajay | Major
18 | Any Solution -> Request For PoC -> Problem Statement Field | Problem Statement Field | Any Solution PoC Form | It should accept Space, special characters and numbers | Only accepting alphabets | Active | Ajay | Major
19 | Any Solution -> Request For PoC -> Solution Description Field | Solution Description Field | Any Solution PoC Form | It should accept Space, special characters and numbers | Only accepting alphabets | Active | Ajay | Major
20 | Any Solution -> Request For PoC -> Primary SPoC Name Field | Primary SPoC Name Field | Any Solution PoC Form | It should accept Space, special characters and numbers | Only accepting alphabets | Active | Ajay | Major
21 | Any Solution -> Request For PoC -> SPoC Contact Number Field | SPoC Contact Number Field | Any Solution PoC Form | More than 10 should be allowed because international clients can contact with their international codes | Allowed only 10 characters currently | Active | Ajay | Minor
22 | Newsletter | Newsletter Mail | https://mosaicthings.lntinfotech.com/newsletter | Mail should come from @lntinfotech.com | But currently coming from mosaic.things.iot@gmail.com | Active | Satej | Major
23 | Landing page -> Recognitions Section | Recognition Section in Landing Page | https://ltimosaicthingsdev.azurewebsites.net/landing | Recognition Section should be properly visible | Recognition Section is hiding somewhere | Active | Ajay | Major
24 | Marketplace -> Search box | Search box functionality | https://ltimosaicthingsdev.azurewebsites.net/solution | When click search text box and then click outside the box then below textbox it says "Search key is required." Firstly it should be in white color or text should be visible | Currently Red color is present whis is not visible clearly | Active | Ajay | Major
25 | Landing -> Our Latest Work Section | Our Latest Work Section | https://ltimosaicthingsdev.azurewebsites.net/landing | Images should be clearly visible and Text should be there according to the images change | Currently there are no images and text change according to the images in this section | Active | Ajay | Major
26 | Solution -> upload button -> upload notification | Solution Upload Button | https://ltimosaicthingsdev.azurewebsites.net/solution | When solution goes for admin approval it should notify that your solution will be uploaded after verification by Admin | Currently it is notifying that your solution is uploaded successfully | Active | Ajay | Minor
27 | Admin Portal -> Approve button | On Approve button click notification | https://ltimosaicthingsdev.azurewebsites.net/approval | On Approval notification it should "Approved Successfully" | Currently it says your solution is uploaded successfully | Active | Ajay | Minor
28 | Landing -> Banner | On Banner Image Text | https://ltimosaicthingsdev.azurewebsites.net/landing | Banner text should be vertically centered aligned | Currently it is slightly lower then center | Active | Ajay | Minor
29 | Solution -> Startup Solutions -> Solution 170 | Title text | https://ltimosaicthingsdev.azurewebsites.net/description/170 | Title text should be denoted as dot when character limit exceeds | Currently it is overflow over other text | Active | Ajay | Major
30 | Solution -> Startup Solutions -> Solution 170 | Title text | https://ltimosaicthingsdev.azurewebsites.net/description/170 | When there is long text then it should adjust itself | Currently the screen is moving to the right place and adjusting according to the text. | Active | Ajay | Major
31 | Navigation Top Bar | Workflow Orchestration text | https://ltimosaicthingsdev.azurewebsites.net/landing | Workflow Orchestration text should be centrally aligned to the yellow below line | Workflow orchestration text is left alligned currently | Active | Ajay | Minor
32 | Navigation Top Bar | IIoT in a suitcase text | https://ltimosaicthingsdev.azurewebsites.net/landing | Iiot in a suitcase text should be centrally aligned to the yellow below line | Iiot in a suitcase text is left alligned currently | Active | Ajay | Minor
33 | IIoT in a Suitcase -> detailed solution | Additional Information | https://ltimosaicthingsdev.azurewebsites.net/suitcasesolutiondescription/30 | Two additional information | Only one additional information is shown on ui and api is returning two | Active | Ajay | Major
34 | Navigation Top Bar -> Menu Bar | Menu Bar in navigation Bar | https://ltimosaicthingsdev.azurewebsites.net/landing | Menu Bar is expected to be central aligned | Currently bottom alligned | Active | Ajay | Major
35 | Any Solution -> Video Demo | Video Demo in any solution page | https://ltimosaicthingsdev.azurewebsites.net/landing | we can fast forward the video file | currently we are not able to fast forward our video | Active | Ajay | Major
36 | MarketPlace -> Hamburger Menu | Hamburger menu | https://ltimosaicthingsdev.azurewebsites.net/solution | It should match with the search field | alignement is not perfect | Active | Ajay | Minor
37 | Landing page -> Mosaic Things At A Glance | Mosaic Things At A Glance Yellow Line | https://ltimosaicthingsdev.azurewebsites.net/landing | Yellow line should be there below Mosaic Things At A Glance Text | Currently there is no Yellow line | Active | Ajay | Minor
38 | Landing page -> Recognitions Section | Recognitions Yellow Line | https://ltimosaicthingsdev.azurewebsites.net/landing | Yellow line should be there below Recognitions Text | Currently there is no Yellow line | Active | Ajay | Minor
39 | Landing page -> Our Latest Works -> Learn More | Learn More Button | https://ltimosaicthingsdev.azurewebsites.net/landing | Learn More button radius should be 100% | currently it is not 100% | Active | Ajay | Minor
40 | Solution Upload -> Brief Description | Brief Description text box | https://ltimosaicthingsdev.azurewebsites.net/solution | Only Character limit should be followed | Currently Word limit is followed | Active | Ajay | Minor
41 | Solution Upload -> Description | Description text box | https://ltimosaicthingsdev.azurewebsites.net/solution | Only Character limit should be followed | Currently Word limit is followed | Active | Ajay | Minor
42 | Partners -> Join Us Today Button | Join Us Today Button Color test | https://ltimosaicthingsdev.azurewebsites.net/partner | Color code should be uniformly followed | Currently it is in blue color | Active | Ajay | Minor
43 | Partners -> Join Us Today Button | Join Us Today Button Radius test | https://ltimosaicthingsdev.azurewebsites.net/partner | Button Radius should be 100% | Not properly curved button | Active | Ajay | Minor
44 | Partners -> Our Partners Text | Our Partner Text | https://ltimosaicthingsdev.azurewebsites.net/partner | Our Partner title should be in one line | It is fragmented into two lines | Active | Ajay | Minor
45 | Partners -> Partners Logo | Partners Logo Alignment | https://ltimosaicthingsdev.azurewebsites.net/partner | Partners logos is not centrally aligned | Some are left aligned, some are right aligned and some are bottom aligned. | Active | Ajay | Minor
46 | Partners -> Startup Section | Startup Section both side margin test | https://ltimosaicthingsdev.azurewebsites.net/partner | Section should be perfectly aligned from left and right | Section is more left aligned | Active | Ajay | Minor
47 | Partners -> Startup Section | Platform Partners Section both side margin test | https://ltimosaicthingsdev.azurewebsites.net/partner | Section should be perfectly aligned from left and right | Section is more left aligned | Active | Ajay | Minor
48 | Partners -> Startup Section | Technology Partners Section both side margin test | https://ltimosaicthingsdev.azurewebsites.net/partner | Section should be perfectly aligned from left and right | Section is more left aligned | Active | Ajay | Minor
49 | Partners -> Startup Section | Hardware Partners Section both side margin test | https://ltimosaicthingsdev.azurewebsites.net/partner | Section should be perfectly aligned from left and right | Section is more left aligned | Active | Ajay | Minor
50 | Partners -> Startup Section | Academia Section both side margin test | https://ltimosaicthingsdev.azurewebsites.net/partner | Section should be perfectly aligned from left and right | Section is more left aligned | Active | Ajay | Minor
51 | Partners -> Fill Up The Form To Partner With Us | Fill Up the form to partner with us alignment test | https://ltimosaicthingsdev.azurewebsites.net/partner | One Line Alignment | currently it is in two lines | Active | Ajay | Minor
52 | Partners -> Join Us Today Text | Join Us Today and Fill Up the Form to partner comparision | https://ltimosaicthingsdev.azurewebsites.net/partner | Both is representing only one things so only one should present | Currently both are present | Active | Ajay | Minor
53 | Landing Page - > Mosaic Things At a glance heading | Mosaic Things At A Glance Yellow Line | https://ltimosaicthingsdev.azurewebsites.net/landing | Yellow line should be aligned | Currently it very below than heading | Active | Ajay | Minor
54 | Landing Page - > Recognitions heading | Recognitions Yellow Line | https://ltimosaicthingsdev.azurewebsites.net/landing | Yellow line should be aligned | Currently it very below than heading | Active | Ajay | Minor
55 | Partners Page -> Create your account to access all of LTI's IOT applications, communities, support & more. | Create Your Account text is not valid with sign in text | https://ltimosaicthingsdev.azurewebsites.net/partner | Sign up button is expected with this text | Currently Sign in button is there | Active | Ajay | Minor
56 | Signup Page | After Sign up toast message | https://ltimosaicthingsdev.azurewebsites.net/signup | Toast will come like "Login after admin approval" | Currently you can login after sign up toast is there | Active | Ajay | Major
57 | Welcome Mail | Welcome Mail after sign up | https://ltimosaicthingsdev.azurewebsites.net/signup | Welcome mail should come after admin approval | currently coming after user sign up | Active | Tanmay | Major
58 | Approval Management -> scroll bar | compare scrollbar of past requests and its solution | https://ltimosaicthingsdev.azurewebsites.net/approval | it should be same scrollbar | one is square in shape and other one is circular | Active | Ajay | Minor
59 | When Refreshing | Refresh Test | https://ltimosaicthingsdev.azurewebsites.net/approval | First login screen appears for 1 second then original page redirected |  | Active | Ajay | Major

## Marketplace_Resolved
Bug ID | Sections | Test Case | Steps | Expected | Actual | Status | Part | Bug Priority | Repeated Bugs | Branch Name
1 |  | Solution Upload Button | Clicked On DDM Tab | Label Name should be "Upload" | Label Name "Upload Solution" | Closed
2 |  | Solution Upload Button | Clicked On ICM Tab | Label Name should be "Upload" | Label Name "Upload Solution" | Closed
3 |  | Solution Upload Button | Clicked On Orchestration Tab | Label Name should be "Upload" | Label Name "Upload Solution" | Closed
4 |  | Solution Upload textbox Marketplace | Typing in solution name textbox | should take numeric, space and special character | Only taking alphabet | Closed
5 |  | Solution Upload video Demo File Marketplace | Choosing File from video Demo File | It is not mandatory field for solution Upload | Currently Solution cannot upload without this field | Closed
6 |  | Solution Upload Case Study (PDF FILE) Marketplace | Choosing File from Case Study PDF File | It is not mandatory field for solution Upload | Currently Solution cannot upload without this field | Closed
7 |  | Solution Upload Demo Link Marketplace | On Demo Link in Market Place Solution Upload | It is not mandatory field for solution Upload | Currently Solution cannot upload without this field | Closed
8 |  | Solution Upload MarketPlace Without Image Only | Trying to upload solution without image | Screen should say image is mandatory for solution upload | Validation is there but no notification on screen for image insertion | Closed
9 |  | Solution Upload Marketplace Metatags | Metatags on Market Place Solution Upload | It is not mandatory field for solution Upload | Currently Solution cannot upload without this field | Closed
10 |  | Hardware Upload textbox Marketplace | Typing in Hardware name textbox | should take numeric, space and special character | Only taking alphabet | Closed
11 |  | Hardware Upload video Demo File Marketplace | Choosing File from hardware video Demo File | It is not mandatory field for Hardware Upload | Currently Solution cannot upload without this field | Closed
12 |  | Hardware Upload video PDF File Marketplace | Choosing File from Hardware PDF File | It is not mandatory field for Hardware Upload | Currently Solution cannot upload without this field | Closed
13 |  | Hardware Upload Marketplace Metatags | Metatags on Market Place Hardware Upload | It is not mandatory field for Hardware Upload | Currently Solution cannot upload without this field | Closed
14 |  | Hardware Upload MarketPlace Without Image Only | Trying to upload solution without image | Screen should say image is mandatory for solution upload | Validation is there but no notification on screen for image insertion | Closed
15 |  | Allignment Of Solution Upload Form MarketPlace | Solution Upload In MarketPlace | Allignment should be perfect Of this Page | Allignment is not perfect Of this Page | Closed
16 |  | Approve and Reject on Partner Upload Admin | https://ltimosaicthingsdev.azurewebsites.net/approval | Approve & Reject button should function. | Currently Approve and Reject button is functioning only when I am uploading the same image of logo image url field | Closed
17 |  | Reject Button Functionality in Admin Portal for all Hardware, Solution & etc…. | https://ltimosaicthingsdev.azurewebsites.net/approval | Reject button should convey notification message "Current Submission is rejected Successfully | Reject button notification message "Current Submission is accepted Successfully | Closed
18 |  | Demo link in Admin Module | https://ltimosaicthingsdev.azurewebsites.net/approval | Demo link is not mandatory in Admin Module also | It is Mandatory in Admin Module, hence Approve and Reject is not working | Closed
19 |  | Video File link | Solutions Upload | Video File Link should accept in mp4 format only | Any Format is applicable | Closed
20 |  | Case Study link | Solutions Upload | Case study Link should accept in ppt and pdf format | Any Format is applicable | Closed
21 |  | Image Attachments link | Solutions Upload | Image Attachments should accept in png file format | JPG and any bitmap image files uploading | Closed
22 |  | Video File link | Hardware Upload | Video File Link should accept in mp4 format only | Any Format is applicable | Closed
23 |  | Case Study link | Hardware Upload | Case study Link should accept in ppt and pdf format | Any Format is applicable | Closed
24 |  | Image Attachments link | Hardware Upload | Image Attachments should accept in png file format | JPG and any bitmap image files uploading | Closed
25 |  | Clicking on Solutions | On Any Solutions Page | It should not download the files automatically. | When Clicking some solutions, downloads images, video files and even case study sometimes | Closed
26 |  | Solution Upload MarketPlace Images Sequentiality | Image Selection on Market Place Solution Upload | Image First uploaded should be first on solution page and it should be sequential | Image first uploaded goes to third position and second uploaded goes to first position | Closed
27 |  | Hardware Upload MarketPlace Images Sequentiality | Image Selection on Market Place Solution Upload | Image First uploaded should be first on solution page and it should be sequential | Image first uploaded goes to third position and second uploaded goes to first position | Closed
28 |  | Solution Update Icon Click | https://ltimosaicthingsdev.azurewebsites.net/description/128 | Form should auto populate data in this solution when click on update button near solution name | Form is empty when clicked on update button near solution name | Closed
29 |  | Solution Update Icon Click | https://ltimosaicthingsdev.azurewebsites.net/description/130 | Form should auto populate data in this solution when click on update button near solution name | Form is empty when clicked on update button near solution name | Closed
30 |  | Uploading Case Study File While in updating solution | On Any Solutions Page | Case sudy file should upload | Case study file is not uploading in updating the solution | Closed | Note:- Backend Issue
31 |  | Uploading Image While in updating Solution | On Any Solutions Page | Image file should upload | Image file is not uploading in updating the solution | Closed | Note:- Backend Issue
32 |  | Uploading Video File While in Updating Solution | On Any Solutions Page | Video File should upload in solutions | Video file is not uploading in updating the solution | Closed | Note:- Backend Issue
33 |  | KPI's in Solution Upload | On Any Solution Upload form page | It should accept Space, special characters and numbers | Only accepting alphabets | Closed
34 |  | Business Needs Addressed | On Any Solution Upload form page | It should accept Space, special characters and numbers | Only accepting alphabets | Closed
35 |  | Technological Components Used | On Any Solution Upload form page | It should accept Space, special characters and numbers | Only accepting alphabets | Closed
36 |  | Meta Tags | On Any Solution Upload form page | It should accept Space, special characters and numbers | Only accepting alphabets | Closed
37 |  | Onboard User API Whole Functionality | https://ltimosaicthingsdev.azurewebsites.net/approval | Data should be fetched accordingly | Default Data is there | Closed | Note:- Backend Issue
38 |  | Logo Image URL in Partner Onboard | https://ltimosaicthingsdev.azurewebsites.net/partner | Mention Size of the image next to logo image url (200X100) | No size is mentioned | Closed
39 |  | Email in Partner Onboard | https://ltimosaicthingsdev.azurewebsites.net/partner | Notification for Email Field is necessary | No Notification is there | Closed
40 |  | Website Url in Partner Onboard | https://ltimosaicthingsdev.azurewebsites.net/partner | Notification for Website Url Field is necessary | No Notification is there | Closed
41 |  | Message in Partner Onboard | https://ltimosaicthingsdev.azurewebsites.net/partner | Notification for Message Field is necessary | No Notification is there | Closed
42 |  | Reject Functionality in User Onboard Approval Management | https://ltimosaicthingsdev.azurewebsites.net/approval | When Rejected User should not be in list view | Currently Rejected User is in the list | Closed | Note:- Backend Issue
43 |  | Approve Functionality in User Onboard Approval Management | https://ltimosaicthingsdev.azurewebsites.net/approval | When approved User should not be in list view | Currently approved User is in the list | Closed | Note:- Backend Issue
44 |  | Video Demo File link in Update Solution | https://ltimosaicthingsdev.azurewebsites.net/description/2 | Video File Link should accept in mp4 format only | Any Format is applicable | Closed
45 |  | Case Study File link in Update Solution | https://ltimosaicthingsdev.azurewebsites.net/description/2 | Case study Link should accept in ppt and pdf format | Any Format is applicable | Closed
46 |  | On any Solution Update | On any solution update page like https://ltimosaicthingsdev.azurewebsites.net/description/3 | When updating video file it should forward the same in approval management part. | Currently Video File is not present | Closed | Note:- Backend Issue
47 |  | On any Solution Update | On any solution update page like https://ltimosaicthingsdev.azurewebsites.net/description/3 | When updating case study file it should forward the same in approval management part. | Currently Case Study File is not present | Closed | Note:- Backend Issue
48 |  | On any Solution Update | On any solution update page like https://ltimosaicthingsdev.azurewebsites.net/description/3 | Images should be as usual as update management screen | Images are broken | Closed | Note:- Backend Issue
49 |  | Onboard User Apporval Management | https://ltimosaicthingsdev.azurewebsites.net/approval | In Active Requests and Past Requests User Onboard 'By': name of the user who uploaded should be present | Not showing any name just showing By: N/A on user onboard request | Closed | Note:- Backend Issue
50 |  | Policy Check Box in Partner Onboard | https://ltimosaicthingsdev.azurewebsites.net/partner | Form should not submit if checkbox not checked | Currently submitting if it is not checked | Closed
51 |  | Logo Image URL in Partner Onboard | https://ltimosaicthingsdev.azurewebsites.net/partner | Form should not submit if image is not choosen | Form is currently submitting | Closed
52 |  | Email in Partner Onboard | https://ltimosaicthingsdev.azurewebsites.net/partner | Form should not submit if email field is empty | Form is currently submitting | Closed
53 |  | Reject Functionality in Partner Approval Management | https://ltimosaicthingsdev.azurewebsites.net/approval | When Rejected it should convey message"Rejected Successfully" | Currently convey "User onboarded Successfully" | Closed
54 |  | Thumbnail Image in Any Solution | In Horizontal Scrollview | Update any solution in mosaic things then "thumbNailImage" of the particular Solution should not break | When we update any solution in mosaic things dev environment then "thumbNailImage" of the particular Solution get breaks | Closed
55 |  | Partner Types fields in Partner Onboard Form | https://ltimosaicthingsdev.azurewebsites.net/partner | Partner Type Field should fetch data accordingly through api | Partner Type Field is not fetching data currently | Closed | Satej
56 |  | Image Append in Solution | https://ltimosaicthingsdev.azurewebsites.net/description/148 | Image should not append | Image is appending in solution update | Closed | Satej
57 |  | Video Demo Functionality | Eg:- https://ltimosaicthingsdev.azurewebsites.net/description/148 | Video should buffer and work properly when Video Demo link is clicked | Video file is not running currently | Closed | Ajay/Satej
58 |  | Demo Link To Launch Solution | Eg:-https://ltimosaicthingsdev.azurewebsites.net/description/148 | Demo link should launch the website as the link inputed by user. For eg:- if the website is www.test.com then it should redirect on it | Currently demo link is appending "https://ltimosaicthingsdev.azurewebsites.net/www.test.com" | Closed | Ajay
59 |  | Business Needs Addressed in approval management | https://ltimosaicthingsdev.azurewebsites.net/approval | Business Needs adressed textbox functionaility in solution approval management should work fyn. | Business Needs Adressed textbox is adding in new update and also when I try to cancel that field it is not cancelling | Closed | Ajay
60 |  | Password in Onboard User | In Database | Password database storing issue | Password is not storing in database | Closed | Ajay/Satej
61 |  | Deleting a user in the database | When user deleted from the database |  | Currently when entry get deleted from database then it is showing the user is present with the same email id when we on board the same deleted user with the same email id. | Closed | Satej | Minor
62 |  | Kpi's in Solution Update | In Solution Update | Kpi's should be in bullet form as on mosaicthings.lntinfotech.com | Currently Kpi's are sperated with comma | Closed | Ajay/Satej | Minor
63 |  | Hardware Update Functionality | Update Functionality | It should submit the data on approval management | Hardware Update Submit Button when clicked through internal server error | Closed | Ajay/Satej | Major
64 |  | Demo link | In solution upload | Not accepting .com | Currently not accepting .com | Closed | Ajay | Major
65 |  | Password Validation in Onboard User | https://ltimosaicthingsdev.azurewebsites.net/onboarduser | Password Validation should work like this "Password must contains at least 6 character including Upper/Lower, numbers and special characters (like @)" | Currently there is no validation on user onboard and I am able to enter anything as password | Closed | Ajay | Major
66 | Approval Management -> Active/Past Requests | solution upload in admin module | https://ltimosaicthingsdev.azurewebsites.net/approval | When solution is uploaded through upload solution then solution should pass on admin portal for approval with all the fields filled previously | When solution is uploaded currently solution is empty for the admin so admin needs to refill it and then submit the solution | Closed | Satej | Major
67 |  | First Name in User Management | https://ltimosaicthings.azureedge.net/#/user | Minimum One Character is mandatory | Accepting three minimum characters currently | Closed | Ajay | Major
68 |  | Last Name in User Management | https://ltimosaicthings.azureedge.net/#/user | Minimum One Character is mandatory | Accepting three minimum characters currently | Closed | Ajay | Major
69 |  | Subscription Checkbox in User Management | https://ltimosaicthings.azureedge.net/#/user | This is optional select | Currently it is mandatory for user addition submit | Closed | Ajay | Major
70 | User Management -> Role Selection | On Save Clicked in User Management | https://ltimosaicthings.azureedge.net/#/user | If user role is selected it should save on click | Currently changing user role and saving it is not working | Closed | Backend | Major
71 | User Management -> Toggle Button | Activation Status in User Management | https://ltimosaicthings.azureedge.net/#/user | When toggle button is red then user should not get deleted from that list. | Users get removed currently from all users list if toogle changes to red | Closed | Ajay/Satej | Major |  | 3_Ajay_ui_usermanagement_bugfix_togglebutton
72 | Approval Management -> Active/Past Requests | Solution Name in upload solution in admin portal | https://ltimosaicthingsdev.azurewebsites.net/approval | It should accept Space, special characters and numbers | Only accepting alphabets | Closed | Ajay | Minor | Yes | 4to8_Ajay_ui_approvalmanagement_bugfix_requestform
73 | Approval Management -> Active/Past Requests | KPI's in upload solution in admin portal | https://ltimosaicthingsdev.azurewebsites.net/approval | It should accept Space, special characters and numbers | Only accepting alphabets | Closed | Ajay | Minor | Yes | 4to8_Ajay_ui_approvalmanagement_bugfix_requestform
74 | Approval Management -> Active/Past Requests | Business Needs Addressed in upload solution in admin portal | https://ltimosaicthingsdev.azurewebsites.net/approval | It should accept Space, special characters and numbers | Only accepting alphabets | Closed | Ajay | Minor | Yes | 4to8_Ajay_ui_approvalmanagement_bugfix_requestform
75 | Approval Management -> Active/Past Requests | Technological Components Used in upload solution in admin portal | https://ltimosaicthingsdev.azurewebsites.net/approval | It should accept Space, special characters and numbers | Only accepting alphabets | Closed | Ajay | Minor | Yes | 4to8_Ajay_ui_approvalmanagement_bugfix_requestform
76 | Approval Management -> Active/Past Requests | Meta Tags Used in upload solution in admin portal | https://ltimosaicthingsdev.azurewebsites.net/approval | It should accept Space, special characters and numbers | Only accepting alphabets | Closed | Ajay | Minor | Yes | 4to8_Ajay_ui_approvalmanagement_bugfix_requestform
77 | Approval Management -> Active/Past Requests | Normal Solution Upload or Editing the solution | https://ltimosaicthingsdev.azurewebsites.net/approval | Demo link Functionality is not behaving properly in both Solution Upload or Solution Edit |  | Closed | Ajay | Minor | Yes | 18_Ajay_ui_approvmngmt_bugfix_solndemolink
78 | Marketplace -> Hardware Partner Solutions | Edit button functionality on hardware solutions | https://ltimosaicthingsdev.azurewebsites.net/hardware/166 | Edit Icon should be there besides Hardware Solution Name | There are no edit icons present | Closed | Ajay | Major |  | 19_Ajay_ui_hdwsoln_bugfix_editlinknotpresent
79 | Partners Form | Company Name in Partners | https://ltimosaicthingsdev.azurewebsites.net/partner | It should accept Space, special characters and numbers | Only accepting alphabets | Closed | Ajay | Minor | Yes | 20_Ajay_ui_partners_bugfix_companyname
80 | User Management -> Subscription | Subscription Check Box | https://ltimosaicthings.azureedge.net/landing#/user | subscription mandatory | subscription should not be mandatory | Closed | Ajay | Major | yes | 22_Ajay_ui_usermngmt_bugfix_subscription
81 | Approval Management -> Partners Form | Partners Upload in admin module | https://ltimosaicthingsdev.azurewebsites.net/approval | When Partners is uploaded through Partner Upload then solution should pass on admin portal for approval with all the fields filled previously | When Partner is uploaded currently Partner uploaded is empty for the admin so admin needs to refill it and then submit the solution | Closed | Satej | Major
82 | My Profile Section -> My Info | Save Changes without subscription | https://ltimosaicthingsdev.azurewebsites.net/myprofile | Changes to be save without subscription of both newsletter and full features | Changes are not saving currently we need to select one particular checkbox currently only then it is saving | Closed | Ajay | Major |  | 9to17_Ajay_ui_myprofile_bugfix_subscriptionandpwd
83 | My Profile Section -> My Info | Avatar Image | https://ltimosaicthingsdev.azurewebsites.net/myprofile | Avatar Images when saved is not showing in any screens. | Avatar Image is attaching currently but not saving in database | Closed | Backend - giving 400 error | Major
84 | My Profile Section - >Password Settings | New Password Field | https://ltimosaicthingsdev.azurewebsites.net/myprofile | New Password Field should consist of normal password guideline of market place | Currently there is no validation on password fields | Closed | Ajay | Major |  | 9to17_Ajay_ui_myprofile_bugfix_subscriptionandpwd
85 | My Profile Section - >Password Settings | Confirm Password Field | https://ltimosaicthingsdev.azurewebsites.net/myprofile | Confirm Password Field should consist of matching functionality with New Password Field | Currently there is no validation on password fields | Closed | Ajay | Major |  | 9to17_Ajay_ui_myprofile_bugfix_subscriptionandpwd
86 | My Profile Section - >Password Settings | Current Password Field | https://ltimosaicthingsdev.azurewebsites.net/myprofile | Current password should be hidden | Not hidden currently | Closed | Ajay | Minor |  | 9to17_Ajay_ui_myprofile_bugfix_subscriptionandpwd
87 | My Profile Section - >Password Settings | New Password Field | https://ltimosaicthingsdev.azurewebsites.net/myprofile | New password should be hidden | Not hidden currently | Closed | Ajay | Minor |  | 9to17_Ajay_ui_myprofile_bugfix_subscriptionandpwd
88 | My Profile Section - >Password Settings | Confirm Password Field | https://ltimosaicthingsdev.azurewebsites.net/myprofile | Confirm password should be hidden | Not hidden currently | Closed | Ajay | Minor |  | 9to17_Ajay_ui_myprofile_bugfix_subscriptionandpwd

## Penetration_bugs
Bug ID | Test Case | Risk | Abstract | Impact | Affected Domain | Ease of Exploitation | Status | Comments | Attached Images | Comments
1 | Insecure Direct Object References | High | IDOR is a vulnerability when user can successfully access to a webpage, a data object, or a file that they should not have access to without login or rights. Without an access control check, attackers can manipulate these references to access unauthorized data. Policy created by a user should be accessible by that user only. | Any user can access to the other user's data or normal user getting access of tabs and functionalities provided to Admin user then all the confidential data will be disclosed. He can perform malicious activities like changing the user’s data, approving or rejecting the user’s registration request, changing the project related data etc. | http://mosaicthings.lntinfotech.com/analytics | Easy | Resolved | Now analytics page is only accessible with admin login only. |  | Now Anyone cannot see the analytics page without login or without having admin credentials.
2 | Weak Password Policy with Rate Limiting Missing | Medium | The application has weak password policy which is allowing user to set password with weak combinations. A weak password is short, common, a system default, or something that could be rapidly guessed by executing a brute force attack using a subset of all possible passwords, such as words in the dictionary, proper names, words based on the user name or common variations on these themes. The weakness occurs when the application does not check complexity or minimum length of the provided passwords. Weak password requirements allow users to create weak passwords, susceptible to a variety of attacks | This vulnerability presents a medium risk to the business since client-side validation is there, but it doesn’t enforce a strong password policy and sets easily guessable passwords with no account lockout implemented after many wrong login attempts. Since an attacker can take several false login attempts to guess the password, an attacker can launch an automated Brute Force attack on the login page to crack usernames and password of the users and gain unauthorized access to the application. | http://mosaicthings.lntinfotech.com/signin | Moderate | Resolved | We have our own Password policy "Password must contain at least 6 characters, including UPPER/lowercase,numbers and special char(like @)" |  | Our Password Policy includes "Password must contain at least 6 characters, including UPPER/lowercase,numbers and special char(like @)"
3 | Unrestricted File Upload | Medium | If the attacker can upload malicious file to a directory and cause these files to be passed to a code interpreter, without validating content of the file then they can cause malicious code contained in these files to execute on the server. Even if a program stores uploaded files under a directory that isn't accessible from the web, attackers might still be able to leverage the ability to introduce malicious content into the server environment to mount other attacks. During the assessment it was found that executable file is getting uploaded and also file with the double extension. | The consequences of unrestricted file upload can vary, including complete system takeover, an overloaded file system, forwarding attacks to backend systems, and simple defacement. It depends on what the application does with the uploaded file, including where it is stored. | http://mosaicthings.lntinfotech.com/partner | Moderate | Resolved | This is done |  | Nobody can upload any .exe files or in respective fields only field file will be uploaded.
4 | Application is vulnerable to Clickjacking Attack | Medium | Clickjacking is a malicious technique of tricking web users into revealing confidential information or taking control of their computers while clicking on seemingly innocuous web pages. During the assessment it was found that the application is allowing pages to load in frames causing vulnerable to clickjacking attack. | An attacker can trick the victim into malicious actions using frames. An attacker may try to make the trusted window transparent. The attacker will then overlay the trusted window on top of something that the user wants to click on. This causes the end-user to believe that they are clicking on the content that is positioned below the trusted window. Clickjacking enables an attacker to spoof contents, steal cookies and data modification | http://mosaicthings.lntinfotech.com/ | Moderate | Resolved | This is done |  | This is done
5 | HTTPS Not Enforced | Low | The application fails to prevent users from connecting to it over unencrypted connections. HTTP communication is insecure for transmitting sensitive information. This attack is performed by rewriting HTTPS links as HTTP, so that if a targeted user follows a link to the site from an HTTP page, their browser never attempts to use an encrypted connection. To exploit this vulnerability, an attacker must be suitably positioned to intercept and modify the victim's network traffic. This scenario typically occurs when a client communicates with the server over an insecure connection such as public Wi-Fi, or a corporate or home network that is shared with a compromised computer. An attacker situated in the user's ISP or the application's hosting infrastructure could also perform this attack. | An attacker can use network sniffer tools to perform Man in the Middle Attack in order to capture HTTP requests/responses, which contains the cookie in clear text format of a logged in user. If an attacker performs a man in the middle attack, sensitive information can be stolen or modified during the communication without the end user’s knowledge which may lead to identity theft or fraud. | http://mosaicthings.lntinfotech.com | Difficult | Resolved | This is done |  | This is done
6 | Concurrent Session Allowed | Low | Application allows Concurrent Sessions and when logged out of one browser the session remains active on other. The weakness allows multiple valid tokens to be concurrently assigned to the same user account. During the assessment we found that application is allowing multiple concurrent sessions. | If a user appears to be using two different sessions simultaneously, this usually indicates that a security compromise has occurred: either the user has disclosed their credentials to another party, or an attacker has obtained their credentials through some other means. In both cases, permitting concurrent sessions is undesirable because it allows users to persist in undesirable practices without inconvenience and if an attacker somehow steals a user's credentials and the user is already logged in, the attacker immediately tries to log in with the stolen credentials without risk of detection. | http://mosaicthings.lntinfotech.com | Difficult | Active | This is done |  | This is done
7 | Cookie Attributes are Not Set | Low | Using the HttpOnly flag when generating a cookie helps in mitigating the risk of client-side script accessing the protected cookie. If a browser does not support HttpOnly and a website attempts to set an HttpOnly cookie, the HttpOnly flag will be ignored by the browser. The server does not make the cookie secure by encryption or any mechanism when setting the cookie on the client side because of which the cookie is transmitted through insecure channels too. During the assessment it was found that application cookie is missing HTTPOnly and Secure flags. | The attacker can send a valid link with an http instead of https to the victim, since the Secure attribute is not set, the cookie gets transmitted in clear text when the victim clicks the link. This request can be captured by the attacker using various sniffing tools. Since HttpOnly attribute is not set the cookie can be accessed through client-side script | http://mosaicthings.lntinfotech.com | Difficult | Resolved | This is done |  | This is done
8 | TLS version 1.0 Enabled | Low | Website uses TLS to secure all communications between their servers and web browsers. During the testing it was found that the application supports TLS version1.0. The remote host supports the use of SSL ciphers that offer medium strength encryption. TLS 1.0 has many cryptographic design flaws. TLS 1.0 has been deprecated and due to pervasive security flaws, it is not recommended for use. If plaintext is repeatedly encrypted (e.g., HTTP cookies), and an attacker can obtain many (i.e., tens of millions) ciphertexts, the attacker may be able to derive the plaintext. | An attacker may be able to exploit these issues to conduct man-in-the-middle attacks or decrypt communications between the affected service and clients. | http://mosaicthings.lntinfotech.com | Difficult | Resolved | Already this is done, We are using 1.2 TLS Version Please refer the screenshot. We are not able to detect where 1.0 TLS Version is in the system. |  | In our azure server we are using TLS 1.2. Refer the screenshot please.
9 | Cleartext Credentials in Browser Memory | Low | If credentials entered by the user are stored in browser memory in clear text then it can be easily read by the attacker, who gets the access to victim’s open browser session, using memory reading tools like WinHex. During the assessment it was found that the credentials entered by the user are being stored in browser memory in clear text. | If an attacker gets the login credentials, then he/she can easily login into victim's account as an authenticated and legitimate user and can perform malicious actions and modifications in the victim's profile. | http://mosaicthings.lntinfotech.com | Difficult | Resolved | This is done |  | This is done
10 | No Session Timeout | Low | The application does not terminate the session automatically even if the user session is inactive for a prolonged period after login | A malicious user who has physical access to the system could gain access to an already active session and perform actions as a legitimate user. | http://mosaicthings.lntinfotech.com | Difficult | Resolved | Our session Time out policy is one day. Kindly Test accordingly. |  | Our session time out policy includes 24 hours kindly test accordingly.
11 | Information Disclosure through Default Banner | Low | The default banner leaks the version information of the application platform. This information may prove vital for launch further attacks. During the time of assessment, it was observed that, server information MicrosoftIIS/10.0 is reflected in response headers. | Default banner leaks vital information such as version information, which may help an attacker to launch specific exploits for the vulnerability associate with the application version. | https://ltimosicthigs.azurewebsites.net | Difficult | Resolved | This is done |  | This is done.
12 | No Input Validation | Low | The most common web application security weakness is the failure to properly validate input from the client or environment. This weakness leads to almost all the major vulnerabilities in applications. During the assessment we were able to insert the scripts containing the special characters in various input and search fields. | If the application does not escape special characters in the input and reflects user input as it is back to the browser, an attacker may be able to launch Cross-Site Scripting (XSS) and SQL injection attacks successfully. | http://mosaicthings.lntinfotech.com/icm | Difficult | Resolved | This is done |  | This is done.

## Work_Bench - Phase 1
Bug ID | Sections | Test Case | Steps | Expected | Actual | Status | Part | Bug Priority | Comments | Branch Name
1 | Workbench -> Customer -> New Requests | Tiny MCE | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | This Actual pop up should not be there because of the api key. | The domain is not supported by your API key. Please review your domain settings here. | Resolved | Ashish | Major
2 | Workbench -> Customer -> New Requests | Form Validations For fields | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | Form Validations should be present | No form validations are present | Resolved | Prasenjit | Major
3 | Workbench -> Customer -> New Requests -> Calender Choose Option | Calender Validations | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | Calender date should only be choosen by calender date time function | Currently we can write down the date in that calender field | Resolved | Ashish | Major
4 | Workbench -> Customer -> New Requests | Project Type Selection | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | When Project type like PoC select the user than this goes to next screen but when customer click on back button then it deselects the PoC option | currently it deselect the option | Resolved | Ashish | Minor
5 | Workbench -> Customer -> New Requests | Project Type Selection | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | each screen should forward after prior validations | each screen should forward after prior validations to happen for example without selecting project type we can forward the screens | Resolved | Prasenjit | Major
6 | Workbench -> Developer | Developer Screens | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Nothing is developed till now | There is no prior flow for Developer Screens. | Resolved | Prasenjit | Major
7 | Workbench -> Customer | Requests Screen | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin | When customer screen has no requests then the screen should say "You do not appear to have any request available at this time" | Simple white page | Resolved | Ashish | Minor
8 | Workbench | Notification icons on All Workbench Screens | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin | Notifications icons can be there only when the functionality is working | Please remove currently all notifications Icons on all respective screens | Resolved | Ashish | Minor
10 | Workbench -> Customer | select request type design | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | The design should be centern align or some where above or below the personal info section tab | Currently design is not upto the mark | Resolved | Ashish | Major
11 | Workbench -> Customer | Contact Number Field | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | Contact Field Validation is upto 15 digit is valid with country code field | Currently Contact field is not upto the mark and can be inputted by unlimited number of characters | Resolved | Ashish | Major
12 | Workbench -> Landing | Yellow Line In Sub Headings | https://ltimosaicthingsdev.azurewebsites.net/workbench | Line should be pointed beneath the work title | Line is collapsing | Resolved | Ashish | Minor
13 | Workbench -> Landing | How It Works Section | https://ltimosaicthingsdev.azurewebsites.net/workbench | How It Works Section should be visible in One Screen Resolution | Currently It is not Visible in One Screen Completely in 1366 * 768 | Resolved | Ashish | Minor
14 | Workbench -> Landing | How It Works Section | https://ltimosaicthingsdev.azurewebsites.net/workbench | Numbering in this section should be visible | Numbering is currently not visible in this Section | Resolved | Rachit | Minor
15 | Workbench -> Developer | Count | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Api should return proper count | Currently Api is not returning it's value | Resolved | Tanmay | Major
16 | Workbench -> Customer | Status Column For customer submission | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100065 | Submitted Value should change according to customer selection | Submitted Value is in-review process only | Resolved | Prasenjit | Major
18 | Workbench -> Customer | Router Mismatch | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100065 | After Submission it should only popup and change accordingly values. | Currently it is routing to "https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin" | Resolved | Ashish | Major
19 | Workbench -> Developer | Horizontal Scrollable | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Horizontal Scrollable should not be there | Horizontal Scrollable bar is there in developer screens | Resolved | Ashish | Major
20 | Workbench -> Admin | Status Column For Admin submission | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100065 | Submitted Value should change according to admin selection or should be viewed as customer selection value. | Submitted Value is in-review process only | Resolved | Prasenjit | Major
21 | Workbench -> Developer | Upload Functionality | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Upload should be working for large files | Upload is not working for large files | Resolved | Tanmay | Major | Cheked Uptil 5mb
22 | Workbench -> Customer | Requirement Info By Switching Tabs | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100072 | Switching tabs with submissions should gather the same data from api | When switching Tab with submissions then requirement info values are hiding | Resolved | Prasenjit | Major
23 | Workbench -> Admin | Requirement Info By Switching Tabs | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100072 | Switching tabs with submissions should gather the same data from api | When switching Tab with submissions then requirement info values are hiding | Resolved | Prasenjit | Major
24 | Workbench -> Admin | CreatedOn & RequestedOn Mismatch | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100072 | createdon should be the date on which customer is creating that project | Currenlty there is mismatch on CreatedOn & RequestedOn | Resolved | Prasenjit | Major
25 | Workbench -> Customer | Calender Date Selection | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | Calender Validation for back date selection should not be there | Calender Validations for previous date selection is valid | Resolved | Prasenjit, Tanmay | Minor
26 | Workbench -> Customer | Project Name Validation | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100073 | Character Limit should be of 50 characters at max | Character Limit is not fixed in Project Name Validations | Resolved | Prasenjit | Minor
27 | Workbench -> Customer | When Admin Marks Completed for Customer | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100075 | When Admin Marks status completed or rejected for customer solution then developer submitted options should disable | Currently Customer can change the status | Resolved | Prasenjit, Tanmay | Minor
28 | Workbench -> Developer | On Completion Date End | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | When Completion Date passes by then the entry should get deleted from the developer list | Currently Completion Date Passes by but developer can provide the solution for the same | Dispute | Tanmay | Major | The Ui Field will be changed to Expected Completion Date
29 | Workbench -> admin | Project Submission Status Column | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100074 | Status should not be in textbox | Currently Status is in drop-down | Resolved | prasenjit | Minor
30 | Workbench -> Customer | Submissions Tab on Pending and Rejected | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100066 | When Rejected or Pending status on customer screen cannot show submissions tab | Currently it is visible | Active | Prasenjit | Minor
31 | Workbench -> Developer | Logo Image in All Project Details | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Logo Image should be there in Project Details Section | Not there currently | Active | Prasenjit | Minor
32 | Workbench -> admin | On Active Button Submitted | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin | Active button should respond only with popup like Your request is currently active | Currently Unable to create popup is showing in that screen | Active | Prasenjit | Major
33 | Workbench -> Developer | Count Check | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Count should be fetched according to the api data | Currently count is zero | Active | Prasenjit | Major

## Work_Bench - Phase 2
Bug ID | Sections | Test Case | Steps | Expected | Actual | Status | Part | Bug Priority | Comments | Branch Name
1 | Workbench - > Customer | Breadcrumbs | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin | Breadcrums should be present on each screens. | Currently Breadcrums is not there in the designs. | Done | Prasenjit | Major | done for customer
2 | Workbench - > Customer | Technology Preferneces | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | We can add C++, C# so basically with special characters user can enter technology preferences | Not able to add special characters in this field | Done | Prasenjit | Major | done for customer
3 | Workbench - > Customer | Technology Preferneces | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100089 | Space should also provide the facility to seprate them into the boxes | Currently this facility is basically on comma seperated values | Done | Prasenjit | Major | conflict , some languages or perference might have space in them , eg:ASP.NET MVC, ASP.Net Core.
4 | Workbench - > Admin | Breadcrumbs | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin | Breadcrums should be present on each screens. | Currently Breadcrums is not there in the designs. | Done | Prasenjit | Major | in progress
5 | Workbench - > Admin | Navigating Summary Tasks | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Icons color should change when navigating to different icons in tasks tab | Not changing icon colors | Done | Prasenjit | Minor | done
6 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Task Heading Color should be bold | Currently Normal | Done | Prasenjit | Minor | done
7 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Task Dialog Box Headers are much bolder and bigger in size. | Not Normal make it small and reduce the sizes | Done | Prasenjit | Minor | done
8 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Task drop down menus, field input options should be small in size..It should not be much scrollabel | Currently Whole form is much bigger and not according to the design | Done | Prasenjit | Minor | done (Some conflicts may be there)
9 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Validations should be there in name tags | Currently no validations are there in name tags | Done | Prasenjit | Major | done
10 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Task status should say select initially | Currently Task Status is blank | Done | Prasenjit | Major | done
11 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Task Type should say select initially | Currently Task Type is blank | Done | Prasenjit | Major | done
12 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | In Technology Section of the form select should be perfectly alligned | Bottom alligned | Done | Prasenjit | Minor | done
13 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Description Dialog Box should be large as per the design | Too Small | Done | Prasenjit | Minor | done
14 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | When choosing any technology aspect then it should be aligned too | Bottom alligned | Done | Prasenjit | Minor | done
15 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Arrow in Technology should be center alligned | Bottom alligned | Done | Prasenjit | Minor | done
16 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | When Main Scrollbar is at center and when we select calender, Calender should not change according to the movement of scrollbar | Currently Behaving unexpectedly | Done | Prasenjit | Major | in progress
17 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Technology should return count how many is selected | Currently it shows all tech options selected | Done | Prasenjit | Major | currently the design is changed to show names
18 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Calender Validations should be there | No Calender Validations currently | Done | Prasenjit | Major | in progress
19 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | GitHub' should be written..Please follow design guidelines | Git Hub is written in form | Done | Prasenjit | Minor | done
20 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Cancel button text should be center alligned | Bottom alligned | Done | Prasenjit | Minor | done
21 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Create button text should be center alligned | Bottom alligned | Done | Prasenjit | Minor | done
21 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | If technology is selected max 4 then it should tell user that it cannot add more | Currently no user interaction in this technology Form Segment | Done | Prasenjit | Minor | need to check , default an node library is used
22 | Workbench - > Admin | Status | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Request Status it is | Project status currently | Done | Prasenjit | Minor | conflict -> told to keep Project Status (Need to ask Pankaj)
22 | Workbench - > Admin | Status | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Request Status it is | Project status currently | Done | Prasenjit | Minor | Repeated
23 | Workbench - > Admin | Backlog Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Design is not appropriate | Please go throw the design made by Rachit | Done | Prasenjit | Major | done
24 | Workbench - > Admin | Backlog Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | When inputed 2 digit value in calender then design should not get distorted | Design get distorted | Done | Prasenjit | Major | date 2digit fixed
25 | Workbench - > Admin | Backlog Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Design tab should be small | It is very large currently | Done | Prasenjit | Major | done
26 | Workbench - > Admin | Task Dialog Box Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Form Validations should be present | Currently no form validations is not present | Done | Prasenjit | Major
27 | Workbench - > Admin | Numbering System | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Numbering system should be based on the design | Not Following the current design | Done | Prasenjit | Major | Showing (0 infornt of digit is not proper)
28 | Workbench - > Admin | Icons and text in Summary | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Icons and text should be small as per the design | Not Following the current design | Done | Prasenjit | Major | done
29 | Workbench - > Admin | Line Between Design Icon and Task Subject | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | Line should be there between both mentioned | Not there | Done | Prasenjit | Minor | done
30 | Workbench - > Admin | Task Subject and Technologies | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | Check the design it is currently centered alligned | Upward alligned currently | Done | Prasenjit | Minor | done
31 | Workbench - > Admin | Registration Start & End Date | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | Registration Start & End Date design is not appropriate and it is breaking | Design is breaking due to start and end date pointers | Done | Prasenjit | Major | done
32 | Workbench - > Admin | Text in Green box dropbox | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | Text should be centered allign | left alligned currently | Done | Prasenjit | Minor | done
33 | Workbench - > Admin | Pop up Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | Technology section should fetch technologies accordingly | Currently not fetching | Done | Prasenjit | Major | DONE : (Note: technology stack output format for taskdetails was from api was different , now its object( the changes are done to show tech stack)
34 | Workbench - > Admin | Pop up Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | Customer review option should be working | Not Working | Done | Prasenjit | Major | conflict need to discuss
35 | Workbench - > Admin | No Option to create In-Review Requests | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | In-Review Section Has no Pathways to enter any requests yet | Currently Empty | Active | Prasenjit | Major | in-review done
36 | Workbench - > Admin | Active Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Design is not appropriate for card list | Please go throw the design made by Rachit | Done | Prasenjit | Major | done
37 | Workbench - > Admin | Active Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | When inputed 2 digit value in calender then design should not get distorted | Design get distorted | Done | Prasenjit | Major | done
38 | Workbench - > Admin | Active Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Design tab should be small | It is very large currently | Done | Prasenjit | Major | done
39 | Workbench - > Admin | Completed Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Design is not appropriate | Please go throw the design made by Rachit | Done | Prasenjit | Major | done
40 | Workbench - > Admin | Completed Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | When inputed 2 digit value in calender then design should not get distorted | Design get distorted | Done | Prasenjit | Major | done
41 | Workbench - > Admin | Completed Design | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100089 | Design tab should be small | It is very large currently | Done | Prasenjit | Major | done
42 | Workbench - > Admin | In Review Section Missing in Pop Up Form | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/taskdetails/100094 | In Review should be there in Status Column in Pop-up Form | Currently Missing | Done | Prasenjit | Major | done (New In Review status added )
43 | Workbench - > Admin | Reject | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/newprojectdetails/100090 | Cancel and Reject button should be alligned as per the design | Currenlty Not alligned correctly | Done | Prasenjit | Minor | done
44 | Workbench -> Customer -> New Request Creation | Request Type Screen Match Mismatch | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | pov, poc, capability,usecase is not middled in the center | User request design is not appropriate currenlty | Done | Prasenjit | Minor
45 | Workbench -> Customer -> New Request Creation | Request Type Screen Match Mismatch | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | pov should be point of view , poc should be point of concept the data should be written in full form | Currently Short Form | Done | Prasenjit | Minor
46 | Workbench -> Developer -> Submitted Tab | In Submitted Tab | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | submitted button should be there for new solutions submitted | Currenlty any status is not coming | Done | Prasenjit | Major
47 | Customer -> Any Solution -> Submissions Tab | When Any Solution submitted by developer then submission tab on customer screen | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/requestdetails/100094 | Submissions should be there when developers submit solutions | Developer is submitting Not handled on customer end | Done | Prasenjit | Major
48 | Customer -> New Request -> Technology Preferences |  | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/newrequest | Notification should be there for comma seperated value | Currently no notification is there | Done | Prasenjit | Minor
49 | Admin -> Task -> Backlogs | Task Type | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100101 | Task Type should be the value that should be retrieved in all tasks listed in backlogs | Currently Design text is all there everywhere | Done | Prasenjit | Major
50 | Admin -> Task -> Backlogs | Task Type | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100101 | Icons should change according to the task type | Design icon is all there in all screens | Done | Prasenjit | Major
51 | Admin -> Task -> In Review Tab | In Review Count | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100101 | Count Should be In Review + Customer Review + Review In Progress + Review Done | Currently Count is following only In Review | Done | Prasenjit | Major
52 | Developer -> Task -> Open For Registration | Count Issue | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev/workbenchtask | Count for open for registration is wrong | Currently Count is Wrong | Done | Prasenjit | Major
53 | Developer -> Task -> Registered Task | When Date got exhausted | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev/workbenchtask | When Date got exhausted then task should not be there or Button should got disable | Currently Button is not disable | Done | Prasenjit | Major
54 | Developer -> Task ->All Type Drop Down | All Type Drop Down | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev/workbenchtask | All type drop down should have options | Currently no options | Done | Prasenjit | Major
55 | Admin -> Backlog -> Any Tasks -> Task Form Status | Task form Status | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100101 | Only Admin is capable to provide Active Status from the backlogs | Currently all the options available | Done | Prasenjit | Major
56 | Admin -> Reject | Reject Request Dialog Box | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/newprojectdetails/100114 | when long text is there in rejected then it should notify just saying information is too long or there should be word indicator | Currenlty When detailed text is there then it is showing unable to update | Done | Prasenjit | Major
57 | Admin -> New Task | Task Form Status | https://ltimosaicthingsdev.azurewebsites.net/workbenchadmin/activeprojectdetails/100113 | Calender Date Submission Place holder and date putting is not matching | Calender Date Submission Place holder is in format dd/mm/yy but currently date is putting in format mm/dd/yy | Done | Prasenjit | Minor
58 | Developer -> submission tab | When submission not started | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev/workbenchtask | When submission not started then upload & submit button should disable in developer screen | Currenlty not disabled | Done | Prasenjit | Major
59 | My Requests -> Request Details -> Task -> Submission | When Review Status is In-review | https://ltimosaicthingsdev.azurewebsites.net/workbenchloggedin/taskdetails/100135 | When Inreview is in dropdown submission then complete should be disable | Currently it is not disabled | Done | Prasenjit | Major
60 | Developer -> Nodered -> Github | Github Functionality |  | Url should be open to branches and user should able to update the code in that repository | Not Working Functionality | Active | Shrey + Grao | Major
61 | Developer -> Github | Github Functionality |  | Url should be open to branches and user should able to update the code in that repository | Not Working Functionality | Active | Shrey + Grao | Major
62 | Admin -> Requests -> Tasks | When multiple clicked in Task create button |  | The tasks should be clicked one time and then created | Currently multiple tasks are created with same name if we clicked multiple times | Active | Prasenjit | Major
63 | Developer -> Search | Prepopulated Suggestions Feature |  | Pre-Populated Suggestions should be there in dropdown in search | Not available feature | Active | Prasenjit | Minor
64 | Developer -> Search | If Database is not having that data |  | If Data is not present in database then no task available | Not available feature | Active | Prasenjit | Minor
65 | Developer -> All Type Dropdown | Count change on All Type Dropdown Selection | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev/workbenchtask | Count should get changed when All Type Drop Down Selection will be there | Not available feature | Active | Prasenjit | Minor
66 | Workbench | Navigations and Routings as a whole | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Routings to be got defined | Currently Routings are not defined properly | Active | Prasenjit | Minor
67 | Developer -> Tasks -> Registered -> Github & Nodered Specific Tasks | Github & Nodered Specific Tasks | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | Github Url and Branch name should not be visible until submission date will get started | Not available feature | Done | Prasenjit | Minor
68 | Developer -> Tasks -> Registered -> Upload Solution | Large Files Uploading in both Projects & Tasks | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | When Uploading Large Files there should be upload loader | Not available feature | Active | Prasenjit | Minor
69 | Developer -> Tasks -> Registered -> Upload Solution | Large Files Uploading in both Projects & Tasks | https://ltimosaicthingsdev.azurewebsites.net/workbenchdev | We need to think on uploading Large files more than 5-6 mb because it is not uploading at all | Currently we can upload less than 5mb files | Active | Prasenjit | Minor